June 30, 2009

TO:	APS XAFS School Instructors and Organizers

FROM:	Julie Cross

SUBJECT:	2009 APS XAFS School Timeline

|  | Who does this— ACTION | OUTCOME | DATE COMPLETE |
| --- | --- | --- | --- |
|  | EARLY PLANNING |  |  |
|  | APS XAFS SIG— Form Program Committee | Program committee is S. Calvin, J. Cross, S. Kelly, M. Newville, B. Ravel | 11/25/2008 |
|  | APS XAFS SIG— Identify Local Organizing Committee | J. Cross, N. Lazarz, R. Reed, T. Bolin | 1/30/2009 |
|  | Local Organizing Committee— Recruit Experiment Coordinator | T. Bolin | 1/30/2009 |
|  | Local Organizing Committee— Set dates for School | Dates for School are July 6-10, 2009 | 11/25/2008 |
|  | Local Organizing Committee— Reserve 402/E1100-E1200 and Gallery | Rooms Reserved | 11/25/2008 |
|  | Local Organizing Committee— Set up web page on wiki (http://xafs.org) | School web pages are at http://xafs.org/Workshops/APS2009 | 7/29/2008 |
|  | Program Committee— Write advertising blurb for School | Done. | 7/29/2008 |
|  | Local Organizing Committee— Advertise School (e.g., lightsources.org, SRN, JSR, APS web site, posters, etc.) | Lightsources.org APS User News-At-a-Glance, #52 | 2/23/2009 3/3/2009 |
|  | Local Organizing Committee— Reserve rooms at ANL Guest House | 30 rooms, 7/5 through 7/10 Check-out is Friday, July 10, 20090 | 3/2/2009 |
|  | Program Committee— Begin contacting instructors | Scott Calvin (Sarah Lawrence) Serena DeBeer George (SSRL) | 11/26/2008 |
|  | Experiment Coordinator— Confirm beamline participation | 5 BM, 9 BM, 10 BM, 12 BM, 13 BM, 20 BM, 20 ID | 2/13/2009 |
|  | Program Committee— Set maximum number of participants | Maximum of 30 students, based on 6 beamlines x 5 students/beamline | 2/13/2009 |
|  | 4-8 MONTHS IN ADVANCE |  |  |
|  | Local Organizing Committee— Prepare budget for XSD-ADD (Pam Styka) | Submitted. | 2/23/2009 |
|  | XSD-ADD (Styka)— Set registration fees for ANL and non-ANL Students based on budget | $475 for non-ANL participants $235 for ANL/DOE participants | 3/10/2009 |
|  | XSD-ADD (Styka)— Request ANL Work Project | Charge Code 04576-00-130 -R1 (ANL registration, allowables) -R3 (non-DOE, non-allowables) | 3/11/2009 |
|  | Program Committee— Post working draft of schedule on wiki | Posted. | 3/5/2009 |
|  | Program Committee— Formally invite confirmed instructors | Letters sent to Calvin and Ravel | 3/11/2009 |
|  | Local Organizing Committee— Open web application form (include section for student experiments, odd years only) | http://aps.anl.gov/Users/xafs2009.html | 3/16/2009 |
|  | APS User Administration & Support— Provide copies of The X-Ray Data Booklet and other handouts for participants | Rachel Reed reported that these are no longer in print. | 3/17/09 |
|  | Experiment Coordinator— Apply for beam time | GUP Id: 11910 | 3/4/2009 |
|  | APS User Administration & Support— Enter a beam time request for all participating XAFS beamlines. The User Office needs to do this since the web-based form only allows for a “primary” and two “alternate” beamlines. | Meg Vigliocco-Hagen entered requests for 5 BM-C, 9 BM, 10 BM, 12 BM, 13 BM, 20 BM, and 20 ID. | 3/18/2009 |
|  | Program Committee— Review student applications | Reviewed by Ravel, Cross, Kelly, Ma, Kropf, Newville | 5/20/09 |
|  | Program Committee— Notify students of acceptance (or regrets) | Letters sent by jox@aps.anl.gov | 5/21/09 |
|  | APS User Administration & Support— Verify User Agreements for all participants (odd years only) | Done. Last agreement is for CISA scholar. | 6/23/09 |
|  | AIP Contact Coordinator (Bruce Ravel)— Request AIP support for FIP student | Acceptance letter sent to Tahel El-Hasan, with copy to Amy Flatten (flatten@aps.org) and Michele Irwin (irwin@aps.org) at the American Physical Society | 5/21/09 |
|  | 1-3 MONTHS IN ADVANCE |  |  |
|  | Local Organizing Committee— Make reservations at dinner restaurants | Reza’s, Wednesday, July 8 Aodake, Thursday, July 9 | 3/5/2009 3/5/2009 |
|  | Local Organizing Committee— Plan lunches and snacks | Box lunches from Panera, Bolingbrook. Meeting with catering coordinator 6/29/09. | 6/29/2009 |
|  | Program Committee— Finalize program schedule | Shelly Kelly coordinated the schedule. | 6/16/2009 |
|  | Program Committee— Decide on curricular experiments | Participants will run own samples, as coordinated by beamline scientists. | 5/29/2009 |
|  | Local Organizing Committee— Order coffee supplies | Flavia supplies ordered 6/26/2009 Nespresso supplies ordered 6/28/09 | 6/28/09 |
|  | American Institute of Physics, as advised by Program Committee— Award FIP grant | Awarded to Tayel El-Hasan of Mutah University, Jordan. | 5/21/2009 |
|  | Local Organizing Committee— Reserve ANL buses for dinners | Confirmed | 5/29/2009 |
|  | Local Organizing Committee— Schedule ANL photographer | Confirmed | 5/29/2009 |
|  | Program Committee— Prepare evaluation form | Sent to Nancy Lazarz | 6/30/2009 |
|  | Local Organizing Committee— Secure Welcome and Safety Spiel speakers | J. Murray Gibson—Welcome Paul Rossi—Safety Spiel | 6/5/2009 |
|  | 3-4 WEEKS IN ADVANCE |  |  |
|  | Local Organizing Committee— Order manuals from ANL Media Services | Ordered and received 50 copies, plus three leftover from last year. | 6/16/2009 |
|  | Local Organizing Committee— Order binders and materials for information packet | Nancy ordered these | 6/18/2009 |
|  | Participating Beamline Scientists— Submit ESAFS for beamline experiments. Sample prep lab cut from program. Beamline scientists will discuss sample prep during experiments. | 64104 – 09 BM-B 64026 – 10 BM-B |  |
|  | Local Organizing Committee— Remind to speakers to submit electronic copies of presentations and demonstrations | First notice sent by Matt Newville | 6/22/2009 |
|  | APS User Administration & Support— Request gate passes for participants |  |  |
|  | 1-2 WEEKS IN ADVANCE |  |  |
|  | Local Organizing Committee— Confirm AV equipment | Need to pick up adapter cable and remote control from either Becky Tasker or Bob Whitman on Monday morning. | 6/29/2009 |
|  | Local Organizing Committee— Confirm room set-up | Done. | 6/23/2009 |
|  | Local Organizing Committee— Assemble binders |  |  |
|  | Local Organizing Committee— Buy non-perishable food stuffs |  |  |
|  | Local Organizing Committee— Check stocks of supplies (not enough serving spoons at 2008 school. Also need: duct tape, coffee cups, sugar, creamer, salt, pepper, napkins, plates, eating utensils) |  |  |
|  | Local Organizing Committee— Check supply of power strips, buy more as needed | Power strips will be supplied by the APS User Administration Office (Rachel Reed) | 6/29/2009 |
|  | 3 DAYS IN ADVANCE |  |  |
|  | Local Organizing Committee— Get final head count for dinners | In progress |  |
|  | Local Organizing Committee— Prepare guest lists for dinners | In progress |  |
|  | Local Organizing Committee— Pick up name tags from Conference Services |  |  |
|  | DAY BEFORE THE SCHOOL |  |  |
|  | Local Organizing Committee— Check room set-up |  |  |
|  | Local Organizing Committee— Install power cords in E1100-1200 for computers |  |  |
|  | Local Organizing Committee— Make sure coffee supplies are in place for morning session |  |  |
|  | Local Organizing Committee— Test AV equipment (computer, projector) |  |  |
|  | Local Organizing Committee— Print two copies of schedule to post by E1100-E1200 doors |  |  |
|  | Local Organizing Committee— Print signs for coffee pots, Nespresso menu, etc. |  |  |
|  | DURING THE SCHOOL |  |  |
|  | Local Organizing Committee— File all receipts |  |  |
|  | AFTER THE SCHOOL |  |  |
|  | Local Organizing Committee— Remove power cords and tape from floors |  |  |
|  | Local Organizing Committee— Return AV cable and remote control |  |  |
|  | Program Committee— Send letters of appreciation to speakers, organizers, and helpers |  |  |
|  | Local Organizing Committee— Print copies of student feedback for organizers and instructors |  |  |
|  | Local Organizing Committee— Request reimbursement from Work Project |  |  |

# Footnotes

Experiments at APS beamlines are offered only in odd-number years.